## Project 1
Item | Status | Estimate ( hours) | Description | Remarks
Project plan | G | 1 | Propose an initial plan for the project with the source for data, techniques needed to implement the project, STEPS involved, Performance Metric, How to handle missing values/outliers. | A structured outline has been generated
Dataset | S | 2 | Study the Data Set and Perform ETL Tasks
Helper Functions | N | 2 | Implement Helper functions to cleaning, augmentation, testing |  | G | Done
Baseline Evaluation | N | 3 | Could be MLP's. |  | N | Not started
Testing with Simple Model | N | 3 |  |  | S | Started
Augmented Testing | N | 3 | All the possible rotation, flip, shear,etc
Complex Model With Augmentatinon | N | 3 | CNN preferred
Conclusion | N | 3 | Compare Performance
Deploy on a TF Server/Real system | N | 5 | Implement best model on a real time camera type system. Maybe Flask?
Total |  | 25

## Sheet1
No | Project | Description | Tests | Github
1 | Facial Key Point Detection | Use image processing techniques and deep learning techniques to detect faces in an image and find facial keypoints, such as the position of the eyes, nose, and mouth on a face. | This project tests your knowledge of image processing and feature extraction techniques that allow you to programmatically represent different facial features. You’ll also use your knowledge of deep learning techniques to program a convolutional neural network to recognize facial keypoints. Facial keypoints include points around the eyes, nose, and mouth on any face and are used in many applications, from facial tracking to emotion recognition
2 | Automatic Image Captioning | Combine CNN and RNN knowledge to build a deep learning model that produces captions given an input image | Image captioning requires that you create a complex deep learning model with two components: a CNN that transforms an input image into a set of features, and an RNN that turns those features into rich, descriptive language. In this project, you will implement these cutting-edge deep learning architectures.
3 | Landmark Detection and Tracking | Use feature detection and keypoint descriptors to build a map of the environment with SLAM (simultaneous localization and mapping)
4 | Build a Python Package | This program is all about understanding how to build machine learning algorithms and prepare them for scalable, production systems. A first step towards building these systems is to gain an understanding of writing production level code, which you have the option of doing by writing a Python package of your own. | Key Skills Demonstrated: • Object-oriented programming • Clean and modular code • Code documentation
5 | Deploy a Sentiment Analysis Model | Use your machine learning skills to compare two text sources and identify cases of plagiarism. In this project, you will extract relevant text features and train a model of your own design to do plagiarism detection. Then, you will deploy your trained model using Amazon SageMaker. | Key Skills Demonstrated: • Feature engineering • Model design and evaluation • Model deployment via SageMaker
6 | Dog Breed Classifier Project | • Complete a project to identify dog breeds based on images. | All of the machine learning workflow, from data exploration to model training and evaluation

## Sheet2
| Udacity Course Name | ML
1 | Intro to Descriptive Statistics
2 | Intro to Data Science
3 | Intro to Artificial Intelligence
4 | Reinforcement Learning
5 | Deep Learning
6 | Artificial Intelligence for Robotics
7 | Machine Learning for Trading